## Assignment Usage
Weekly Calendar | All
Data
Task | Task 1 | Resources | Type | Baseline Cost | Cost | Actual Cost | Actual Work | Baseline Budget Cost | Baseline Work | Budget Cost | Budget Work | Actual Overtime Work | Baseline Budget Work | Cumulative Cost | Cumulative Work | Overtime Work | Regular Work | Work
FantasyHockeyProjectorGanntChart | Software Development | Database Server | Work | 0 | 285.0605 | 63.4019 | 78.6333 | 0 | 0 | 0 | 0 | 0 | 0 | 285.0605 | 353.4833 | 0 | 353.4833 | 353.4833
|  | Database Server Total |  | 0 | 285.0605 | 63.4019 | 78.6333 | 0 | 0 | 0 | 0 | 0 | 0 | 285.0605 | 353.4833 | 0 | 353.4833 | 353.4833
| Software Development Total |  |  | 0 | 285.0605 | 63.4019 | 78.6333 | 0 | 0 | 0 | 0 | 0 | 0 | 285.0605 | 353.4833 | 0 | 353.4833 | 353.4833
| Documentation | Nathan Cline | Work | 0 | 3465 | 3465 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 3465 | 99 | 0 | 99 | 99
|  | Nathan Cline Total |  | 0 | 3465 | 3465 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 3465 | 99 | 0 | 99 | 99
|  | Shane O'Toole | Work | 0 | 3220 | 3220 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 3220 | 92 | 0 | 92 | 92
|  | Shane O'Toole Total |  | 0 | 3220 | 3220 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 3220 | 92 | 0 | 92 | 92
| Documentation Total |  |  | 0 | 6685 | 6685 | 191 | 0 | 0 | 0 | 0 | 0 | 0 | 6685 | 191 | 0 | 191 | 191
| Development | Nathan Cline | Work | 0 | 15820 | 2353.75 | 67.25 | 0 | 0 | 0 | 0 | 0 | 0 | 15820 | 452 | 0 | 452 | 452
|  | Nathan Cline Total |  | 0 | 15820 | 2353.75 | 67.25 | 0 | 0 | 0 | 0 | 0 | 0 | 15820 | 452 | 0 | 452 | 452
|  | Shane O'Toole | Work | 0 | 17080 | 2738.75 | 78.25 | 0 | 0 | 0 | 0 | 0 | 0 | 17080 | 488 | 0 | 488 | 488
|  | Shane O'Toole Total |  | 0 | 17080 | 2738.75 | 78.25 | 0 | 0 | 0 | 0 | 0 | 0 | 17080 | 488 | 0 | 488 | 488
|  | Database Server | Work | 0 | 364.5161 | 54.2339 | 67.25 | 0 | 0 | 0 | 0 | 0 | 0 | 364.5161 | 452 | 0 | 452 | 452
|  | Database Server Total |  | 0 | 364.5161 | 54.2339 | 67.25 | 0 | 0 | 0 | 0 | 0 | 0 | 364.5161 | 452 | 0 | 452 | 452
| Development Total |  |  | 0 | 33264.5161 | 5146.7339 | 212.75 | 0 | 0 | 0 | 0 | 0 | 0 | 33264.5161 | 1392 | 0 | 1392 | 1392
| Testing | Unassigned | Work | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Unassigned Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Testing Total |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Debugging | Nathan Cline | Work | 0 | 1260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1260 | 36 | 0 | 36 | 36
|  | Nathan Cline Total |  | 0 | 1260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1260 | 36 | 0 | 36 | 36
|  | Shane O'Toole | Work | 0 | 1260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1260 | 36 | 0 | 36 | 36
|  | Shane O'Toole Total |  | 0 | 1260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1260 | 36 | 0 | 36 | 36
| Debugging Total |  |  | 0 | 2520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2520 | 72 | 0 | 72 | 72
| Practice Presentation | Nathan Cline | Work | 0 | 840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 840 | 24 | 0 | 24 | 24
|  | Nathan Cline Total |  | 0 | 840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 840 | 24 | 0 | 24 | 24
|  | Shane O'Toole | Work | 0 | 840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 840 | 24 | 0 | 24 | 24
|  | Shane O'Toole Total |  | 0 | 840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 840 | 24 | 0 | 24 | 24
| Practice Presentation Total |  |  | 0 | 1680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1680 | 48 | 0 | 48 | 48
FantasyHockeyProjectorGanntChart Total |  |  |  | 0 | 44434.5766 | 11895.1358 | 482.3833 | 0 | 0 | 0 | 0 | 0 | 0 | 44434.5766 | 2056.4833 | 0 | 2056.4833 | 2056.4833
Grand Total |  |  |  | 0 | 44434.5766 | 11895.1358 | 482.3833 | 0 | 0 | 0 | 0 | 0 | 0 | 44434.5766 | 2056.4833 | 0 | 2056.4833 | 2056.4833